| Project Title : PROJEK HOSPITAL PENGAJAR PENGAJAR UNISZA (TENDER TERBUKA - REKA & BINA) |  |
| --- | --- |
| Project No. : | Date : 20.6.2013 |
| Project Mgr : Ir Haizan Bin Hussein |  |

| CATERGORY OF PROJECT |  |  | Likelihood | Impact Rating | Risk Rating |  | Risk Matrix |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Political | 9. Contractual |  | 5. Almost certain | V. Severe | E– Extreme risk, immediate action required |  | LIKELIHOOD | 5 | H | H | H | E | E |
| 2. Scope | 10. Technical |  | 4. Likely | IV. Major | H – High risk, will jeopardize project if not managed |  |  | 4 | M | M | H | E | E |
| 3. Schedule | 11. Environmental |  | 3. Possible | III. Moderate | M – Medium risk, will impact time, cost or quality if not managed |  |  | 3 | L | M | M | H | E |
| 4. Financial | 12. Suppliers |  | 2. Unlikely | II. Minor | L – Low risk, acceptable project management risk, monitor only |  |  | 2 | L | L | M | H | H |
| 5. Human Resources | 13. Industrial relations |  | 1. Rare | I. Insignificant |  |  |  | 1 | L | L | M | M | H |
| 6. Quality | 14. Organisational |  |  |  |  |  |  |  | I | II | III | IV | V |
| 7. Communications | 15. OH & S |  |  |  |  |  |  | IMPACT |  |  |  |  |  |
| 8. Other resources | 16. Cultural |  |  |  |  |  |  |  |  |  |  |  |  |

| Ref No. (WBS) | Risk Event There is a risk that ……….. | Category of Risk | Likelihood Rating | Impact Rating | Risk Rating |
| --- | --- | --- | --- | --- | --- |
|  | Planning & Procurement |  |  |  |  |
|  | - If this sites is chosen then it will affect the cost, time, and quality of the project. | 10 | 5 | v | E |
|  | - If the contract scopes are not clear then it will affect the construction cost and time and quality of the project. | 9 | 4 | IV | E |
|  | - If the safety and health requirements are not properly considered then it will affect the proper function of the hospital. | 15 | 5 | IV | E |
|  | - If the scope is not finalised then it will prolong the planning stage and delay the construction and project completion. | 2 | 4 | IV | E |
|  | - It there is insufficient budget then the project will be delayed | 4 | 4 | IV | E |
|  | - If there is lack of skilled manpower then it will prolong the planning stage and delay the construction and project completion, increase the cost and reduce the quality of the project. | 5 | 5 | III | E |
|  | - If the is an increase in cost s then it might delay the delivery of project s to the client and reduce the quality of the project. | 4 | 5 | III | E |
|  | - If there is ineffective communication between the stakeholders might lead to misunderstanding. | 7 | 3 | III | M |
|  | - If the design cannot meet client’s requirements, the client might not accept the project. | 10 | 3 | IV | H |
|  | - Jika rundingan yuran perunding oleh pihak kontraktor dengan perunding-perunding tidak mengikut norma BEM/LAM dan badan professional yang lain memungkinkan prestasi pihak perunding terjejas. | 4 | 3 | IV | H |
|  | Design Risk |  |  |  |  |
|  | - If need statement is not comprehensive cause changes in design thus delay in design schedule. | 2 | 5 | IV | E |
|  | - If incoherence between ministerial policies and operational procedures- additional scope/cost/changes in design. | 2 | 4 | IV | E |
|  | - If the room data interaction conducted after tender might cause serious cost & design implication | 4 | 5 | IV | E |
|  | - If there is design fault (Arch./M&E/C&S/planner) may cause a lot of defects/building integrity. | 10 | 3 | V | E |
|  | - If design information is not sufficient including the electrical equipment physical load might cause structural failure. | 10 | 3 | IV | H |
|  | - If due to fast changing medical technologies, might cause the out-dated equipment being installed | 10 | 4 | III | H |
|  | - If insufficient design detail – difficulty in construction and increase in cost | 10 | 3 | IV | H |
|  | - If lack of coordination among JKR project team may cause project delay. | 14 | 3 | IV | H |
|  | - If brands/model for medical Equipment offered by Contractor does not of Client’s preference, changes might cause cost implication to the government. | 4 | 3 | III | M |
|  | - If delay in design audit to Contractor might delay in design completion | 10 | 3 | III | M |
|  | - If insufficient space allocated for M&E, might cause difficulty in installation and maintenance of M&E services | 10 | 3 | III | M |
|  | Construction Risk |  |  |  |  |
|  | - If delay in Late Material Approval might cause delay in delivery | 3 | 3 | III | M |
|  | - If there is delay in approval/response and new requirements from local authorities, then may result in redesign and/or delay in implementation. | 7 | 5 | IV | E |
|  | - If there is shortage of manpower (technical staff and skilled labour) then the quality of workmanship will decreased. | 5 | 4 | IV | E |
|  | - If there is delay in delivery of external infra a service by public utilities, then the project schedule will be upset and may delay project delivery. | 3 | 4 | IV | E |
|  | - If changes in end users requirements during construction may require redesign and reworks resulting in delays and variation of works. | 3 | 3 | IV | H |
|  | - If the main Project Director Representative (CM) is not appointed then there may be lack of proper contract management on behalf of government resulting in poor communication and integration. | 5 | 5 | III | H |
|  | - If there is lack of coordination among the specialist contractor and main contractor might cause services clash | 3 | 3 | III | M |
|  | - Jika Kelewatan kontraktor menyiapkan projek mengikut jadual yang ditetapkan boleh menjejaskan perancangan UniSZA dalam memberikan perkhidmatan klinikal dan rawatan serta latihan dan pembelajaran. | 3 | 4 | IV | E |
|  | Handover Risks |  |  |  |  |
|  | - If there is late handover from JKR to client then the DLP will less benefit the client | 3 | 4 | IV | E |
|  | - If the system provided not fully functioning then there will be delayed in handing over | 10 | 4 | IV | E |
|  | - If incomplete or late submission of Project Documentation then it will affect the operation by the client | 9 | 5 | II | H |
|  | - If the issuance of approval by authority is late the handing over will be delayed | 10 | 3 | IV | H |
|  | - If quality of works does not met the specification, then the client will not accept the project (client point of view) resulting in delaying handing over of the project. | 6 | 3 | III | M |

| COMPILED BY: Muhammad Syukri Bin Khasim | SIGNATURE: |
| --- | --- |
| REVIEWED: Ir Haizan Bin Hussein | SIGNATURE: |