## Slide 1: UNIT ECKM BAHAGIAN PENGURUSAN PROJEK KOMPLEKS CAWANGAN PERANCANGAN ASET BERSEPADU
BENGKEL
PROJECT LESSONS LEARNED
CAWANGAN KERJA PENDIDIKAN
JABATAN KERJA RAYA
15 & 17 SEPTEMBER 2021
(Rabu-Jumaat)

## Slide 2
CONTENT
02
#bengkelprojectlessonslearned
HOW TO EFFECTIVELY CAPTURE PLL
ROLES AND RESPONSIBILITIES
PLL PROCESS
WHY PLL ARE INEFFECTIVE?
WHAT IS PROJECT LESSONS LEARNED (PLL)?

## Slide 3
WHAT IS PLL?
03
#bengkelprojectlessonslearned
Project Lessons Learned (PLL) :
is the learning gained
from the process of performing
a task or an activity
To promote
the recurrence
of desirable
outcomes
To prelude
the recurrence
of undesirable
outcomes
Learned the
good practices
Avoid the
repeats of
bad practices
NEW KNOWLEDGE AND NEW LEARNING
are identified through activity & review, and incorporated into future work practices
NEW
LESSONS
BEST PRACTICES
ACTIVITY
activity
review
process
improvement
follow best
practice

## Slide 4
04
#bengkelprojectlessonslearned
Penyiapan Projek 14 dalam 1
PROJEK PEMBINAAN HOSPITAL PENGAJAR UNIVERSITI PUTRA MALAYSIA (HPUPM)
2
Lukisan Siap
Bina (As-Built
Drawing)
7
Skor IBS
80.5 > 70
(column, beam
half slab,
AAC bricks)
1
Sijil Perakuan
Siap Kerja
(CPC)
3
Penyata Akaun
Muktamad
(SOFA)
4
Projek Siap
2 Minggu
Awal
6
Fire Certificate
Diterima
Sebelum CPC
5
Asset Tagging
Bagi 90,250
Bil. Aset
9
Pengiktirafan
QLASSIC
Oleh CIDB
14
Coffee Table Book
Aspire – The
Determination
To Succeed
8
Pengiktirafan
4 Bintang
SHASSIC
Oleh CIDB
10
Pengiktirafan
4 Bintang pHJKR
Oleh
CASKT JKR
11
Zero Major
Defects
13
Penjimatan Kos
Kontrak
(pelanggan dapat
membuat pembelian
tambahan peralatan
perubatan)
12
Lost Time
Injuries (LTI):
Tiada
Kemalangan
Besar Dilaporkan
BEST PRACTICE

## Slide 5
ISU BERULANG DALAM
LAPORAN KETUA AUDIT NEGARA
05
#bengkelprojectlessonslearned
Projek
Lewat Disiapkan
Kualiti Tidak Menepati Spesifikasi
Ketidak-seragaman Penentuan Bon, WJP, Insurans
Tidak Mematuhi Penyediaan Perkhidmatan Kenderaan & Peralatan Melalui Kontrak
Lukisan Siap Bina Berbeza Dari Sebenar, Lewat Dihantar
EOT Diluluskan Di Luar Tempoh Yang Dibenarkan
Kelewatan Tandatangani Dokumen Kontrak
Kelemahan Penyenggaraan Bangunan Pejabat di Putrajaya
Kelemahan Pengurusan Wang Pendahuluan
Pelantikan Semula Kontraktor Yang Telah Ditamatkan
01
02
03
04
05
06
07
08
09
10

## Slide 6
06
#bengkelprojectlessonslearned
BUKU MERAH UPE, JPM

## Slide 7
07
#bengkelprojectlessonslearned
BUKU MERAH UPE, JPM

## Slide 8
12
#bengkelprojectlessonslearned
SA KPKR BIL.17/2018
PENGGUNAAN PLL : JKR GUIDE

## Slide 9
08
#bengkelprojectlessonslearned
PLL REPORTS
Portal JPedia
PROJECT
LESSONS LEARNED REPORTS
Domain PLL Wiki
2018 - 2019

## Slide 10: ISSUES & ELEMENTS Project Lessons Learned
PLL ANALYSIS
09
#bengkelprojectlessonslearned
2019
2018
Two PLL Analysis Workshops were conducted in 2018 and 2019 to analyse the findings from 117 reports.
Both workshops attended by 50 participants from HOPT, HODT, PO’s and Project Team members.

## Slide 11
10
#bengkelprojectlessonslearned
WHAT WHEN WELL
IN PROJECT IMPLEMENTATION
Sistem
Komunikasi
Berkesan
Komitmen Tinggi
Pihak
Berkepentingan
Mesyuarat Tapak/
Penyelarasan
Berkala
Penggunaan
PM Tools
Sistem Pengurusan
Rekod
Sistematik
Ahli Pasukan
Kompeten & Berpengalaman
Bayaran Interim
Berkala
Jadual
Perancangan Lengkap/
Komprehensif

## Slide 12
ISSUES AND REMEDIATION
IN PROJECT IMPLEMENTATION
11
55
29
22
18
25
22
29
75
P
P
P
M
P
M
M
M
M

## Slide 13
Store in central
repisotary
Document &
Compile
Project Learning
PLL ACTIVITIES
13
#bengkelprojectlessonslearned
Capture
Reuse
Apply
Identify (at any
point the asset
life cycle)
Verify & validate
Disseminate/
distribute
Solicit Feedback
Identify Action
Incorporate in
work process
Update related
documents
Archive with
supporting data &
releven documents

## Slide 14
GROUP DISCUSSION
14
#bengkelprojectlessonslearned
PEMBELAJARAN UTAMA
(Key Learnings)
APA
BERLAKU
DENGAN BAIK?
What Went
Well?
APA BOLEH
DILAKUKAN
DENGAN LEBIH
BAIK?
What Could Have
Been Done
Better?
REFER TEMPLATES GIVEN :
Discuss in group this 3 items below

## Slide 15
PLL FORMAT REPORT
15
#bengkelprojectlessonslearned
Exsecutive
Summary
Summarize the methodology, key issues & key lessons learned.
Project
Background
Methodology
Key
Issues
If documented properly, lessons learned provide a powerful method of sharing ideas for improving work processes, operation, quality, safety and cost effectiveness, etc. and helps improve management decision making and worker performance through every phase of a project.
Key Lessons
Learned
Primary
Challenges
Conclusion &
Recommendations
Provide an overview or description of the project.
Step used for capturing, analyzing, validating and communicating PLL.
Summarize all the key issues found from data collections through questionnaire, interview, etc.
List all key lessons learned captured.
Summarize the challenges the team identified for the project.
Conclude and provide the top recommendations Lessons Learned of the project.

## Slide 16: UNIT ECKM BAHAGIAN PENGURUSAN PROJEK KOMPLEKS CAWANGAN PERANCANGAN ASET BERSEPADU
BENGKEL
PROJECT LESSONS LEARNED
SEKIAN TERIMA KASIH