## Sheet1
CKE.GP.12.05.(00).2014
| PENGURUSAN PROJEK | [13 empty] | Rujukan : JKR.PMMM.10
No muka surat: 1
Issue No: 1
| MATRIKS KOMUNIKASI | [13 empty] | Revision No: 0
Tarikh: 07.10.2010
LAPORAN DAN MESYUARAT BERJADUAL
NAMA PROJEK: Hospital Pengajar UniSZA | [8 empty] | DISEDIAKAN OLEH: Muhammad Syukri Bin Khasim
PENGURUS PROJEK : Ir. Haizan Bin Hussein | [8 empty] | TARIKH DISEDIAKAN : 20.6.2013
| PASUKAN HODT ELEKTRIK | [5 empty] | JKR | [6 empty] | KONTRAKTOR | LAIN-LAIN
Personnel Initials | PK CKE | PPR CKE | PPP CKE | KJE BPR A | JEPK BPR A | JEK BPR A | Pengarah Projek | WAKIL Pengarah Projek (E) | HOPT | HODT Mekanikal | HODT Ukur Bahan | HODT Arkitek | HODT Struktur | UTAMA |  | PERUNDING
LAPORAN
Penilaian Teknikal Elektrik |  |  |  | P | M | M
Audit Pembinaan Elektrik |  |  |  | P | M | M | [7 empty] | C |  | C
Consider the reports and meetings required, the subject and frequency (weekly, monthly, milestone, phase)
Abbreviations Key: | P - Prime responsibility for Action | [10 empty] | A – Attends & receives Minutes
| M- Prepares Minutes or Report/distributes | [10 empty] | B – Receives Minutes only
| C – Consulted prior to meetings or report writing | [10 empty] | R– Receives Reports
JKR.PMMM.10
CKE.GP.12.05.(00).2014
| PENGURUSAN PROJEK | [13 empty] | Rujukan : JKR.PMMM.10
No muka surat: 2
Issue No: 1
| MATRIKS KOMUNIKASI | [13 empty] | Revision No: 0
Tarikh: 06.05.2008
LAPORAN DAN MESYUARAT BERJADUAL
NAMA PROJEK: Hospital Pengajar UniSZA | [8 empty] | DISEDIAKAN OLEH: Muhammad Syukri Bin Khasim
PENGURUS PROJEK : Ir. Haizan Bin Hussein | [8 empty] | TARIKH DISEDIAKAN : 20.6.2013
| PASUKAN HODT ELEKTRIK | [5 empty] | JKR | [6 empty] | KONTRAKTOR | LAIN-LAIN
Personnel Initials | PK CKE | PPR CKE | PPP CKE | KJE BPR A | JEPK BPR A | JEK BPR A | Pengarah Projek | Wakil Pengarah Projek (E) | HOPT | HODT Mekanikal | HODT Ukur Bahan | HODT Arkitek | HODT Struktur | UTAMA |  | PERUNDING ELEKTRIK | TNB | TELEKOM
MESYUARAT
Penyelarasan Rekabentuk |  |  |  | C | M | P | [7 empty] | A |  | A
Pra-Pembinaan (Utama) |  |  |  | R | A | A | [7 empty] | C |  | M
Audit Rekabentuk terperinci |  |  |  | C | M | P | [7 empty] | A |  | A
Consider the reports and meetings required, the subject and frequency (weekly, monthly, milestone, phase)
Abbreviations Key: | P - Prime responsibility for Action | [10 empty] | A – Attends & receives Minutes
| M- Prepares Minutes or Report/distributes | [10 empty] | B – Receives Minutes only
| C – Consulted prior to meetings or report writing | [10 empty] | R– Receives Reports
JKR.PMMM.10
Note on G9: asd:
Note on G37: asd:
Note on J9: asd:
Note on J37: asd:
Note on M9: asd:

## Sheet2
PROJECT MANAGEMENT | Reference : | JKR.PMMM.10
| Page No : | 1
| Issue No : | 1
Communication Matrix | Revision No : | 0
| Date : | 06.05.2008