## Slide 1
PROJEK KLINIK KESIHATAN JENIS 3 (CR) DENGAN
KUARTERS RANTAU PANJANG, PASIR MAS
PENGGUNAAN IBS DI TAPAK PROJEK
10 NOVEMBER 2020
Oleh:
JKR Jajahan Pasir Mas, Kelantan

## Slide 2
KEMENTERIAN
KESIHATAN MALAYSIA
KONTRAKTOR
AL RASH CORP. SDN BHD
TARIKH MILIK TAPAK
28 OGOS
2017
TARIKH SIAP KONTRAK
26 NOV.
2020
TEMPOH PROJEK
170
MINGGU
KANDUNGAN TAKLIMAT
Pengenalan Projek
Skop Projek
Penggunaan IBS
Kompenen IBS di KK3
Prosedur Pembinaan
Strategik Kerja JKR PM
Masalah dan Tangani

## Slide 3
PELANGGAN
KEMENTERIAN
KESIHATAN MALAYSIA
PEGAWAI
PENGUASA
PENGARAH JKR NEGERI KELANTAN
KONTRAKTOR
AL RASH CORP. SDN BHD
TARIKH MILIK TAPAK
28 OGOS
2017
TARIKH SIAP KONTRAK
26 NOV.
2020
TEMPOH PROJEK
170
MINGGU
PENGENALAN

## Slide 4
LOKASI
Jarak :
35km dari ibupejabat JKR Kelantan
7km dari pekan Rantau Panjang
Kordinat: LONG LANG
: 06° 00’ 07’’ N
: 102° 00’ 12” E
Menghala ke Pekan Rantau Panjang
Menghala ke bandar Kota Bharu

## Slide 5
SKOP PROJEK BANGUNAN

## Slide 6
PENGUNAAN IBS
Lokasi | Sasaran | Capai
Kuarters | 100 | 100
Klinik | 100 | 100
Pondok Pengawal | 0 | 0
Pencawang TNB | 0 | 0
Rumah Pam | 0 | 0
Rumah Sampah | 0 | 0
Garaj | 0 | 0
Stor | 0 | 0
Jadual penggunaan komponen IBS

## Slide 7
KOMPONEN IBS di KK3
Tiang
Rasuk
Papak
Bata

## Slide 8
JUMLAH IBS di KK3
Bata
Chart: IBS Component at Quartes
| Beam | Column | Slab
 | 72 | 88 | 38
Chart: IBS Component at Clinic
| Beam | Column | Slab
 | 65 | 114 | 20

## Slide 9
PROSEDUR PEMBINAAN
INSTALLATION
DESIGN
FABRICATION
DELIVERY
PLANNING
Diselia oleh Pejabat Tapak

## Slide 10
FABRICATION/ PEMASANGAN

## Slide 11
A
B
C
D
Fabrication Process
Assembly Mould
Mould Cleaning &
Preparation
Fixing Rebar
Final Inspection
Before Casting
E
Concreting
F
Curing
G
Demoulding
H
Final Inspection

## Slide 12
Assembly Mould
Our Practice
Check the flatness of the base mould
Ensure that the dimensions of mould are within the specific tolerances

## Slide 13
Mould Cleaning and Preparation
Practice
The mould should be clean
Form oil or mould release agent should be apply
Check the joint & Edge of mould

## Slide 14
Fixing Rebar
Practice
Check rebar size, spacing & lap length
Rebar, cast in item, corrugated sleeve, lifting hook must be correctly positioned
Sufficient & correct size of spacer

## Slide 15
Final Inspection before casting
Practice
Check & Verify that all
details comply with
Drawing.
TONTON VIDEO

## Slide 16
Concreting
Proper vibration & compaction
Levelling of surface
Conduct Slump Test
Drop height <1m
TONTON VIDEO
TONTON VIDEO

## Slide 17
Curing
Guna admixtures
Lebih 5 jam
15N/mm2, kekuatan minimum yang diperlukan sebelum di-mould

## Slide 18
De-moulding
Loosen & remove all bolts & pins, end & side mould form before lifting

## Slide 19
Check the condition of the finished product
Verify the critical dimension
Proper identification markings should be placed on elements (Code/size/location/weight)
Check the elements have achieved 75% of their design concrete strength before delivery to site
Final Inspection

## Slide 20
Step 1
Delivery
Step 2
Handling
Step 3
Storage
DELIVERY/ PENGHANTARAN

## Slide 21
SEBELUM KELUAR KILANG

## Slide 22
HANDLING/ SEMASA PEMINDAHAN
TONTON VIDEO

## Slide 23
STORAGE/ PENYIMPANAN

## Slide 24
1
2
3
Setting out
Lifting & Installation
Grouting Work
INSTALLATION

## Slide 25
SETTING OUT
Set reference line and offset line to determine the position of precast elements to be installed
Provide level pads ( or shim plates) for setting the level of the elements
Check starter bar

## Slide 26
Lift and rig the panel to its designated location with the use of wire ropes
Adjust panel to position and secure it with diagonal props
Check alignment & Verticality of Element
Adjust temporary prop
Check stability of the erected props before releasing the hoisting cable
LIFTING & INSTALL

## Slide 27
GROUTING WORK
Prepare & apply non-shrink mortal
to seal the gap along bottom edge
of the elements
For corrugated pipe sleeve or splice
sleeve connection, prepare & pour
non- shrink grout into the pipe inlet
provided
Keep the installed elements
undisturbed for at least 24 hrs.

## Slide 28
MATERIAL USED IN INSTALLATION
Neoprene pad
Rubber Strip
Shim Plate

## Slide 29
Neoprene pad
Rubber Strip
Shim Plate

## Slide 30
FOTO SEMASA PEMBINAAN

## Slide 31
STRATEGI KERJA JRK PM DI KK3
Perbincangan
Pemeriksaan
Lawatan
Pelaporan
Taklimat
Audit

## Slide 32
STRATEGI KERJA JRK PM DI KK3
Perbincangan

## Slide 33
STRATEGI KERJA JRK PM DI KK3
Pemeriksaan

## Slide 34
STRATEGI KERJA JRK PM DI KK3
Taklimat

## Slide 35
STRATEGI KERJA JRK PM DI KK3
Audit

## Slide 36
STRATEGI KERJA JRK PM DI KK3
Lawatan

## Slide 37
SUMMARY OF WORK’S DONE FOR IBS COMPONENTS
COMPONENT (A) | TOTAL NOS OF COMPONENTS (B) | DELIVERED ON SITE (C) | BALANCED NOT DELIVERED (B-C) | INSTALLED (D) | BALANCED NOT INSTALLED ON-SITE (C-D)
COLUMN | 88 | 84 | 4 | 47 | 37
BEAM | 72 | 56 | 16 (Upper Roof) | 32 | 20
SLAB | 38 | 38 | 0 | 38 | 0
TOTAL | 198 | 178 | 20 | 117 | 57
BLOCK: KUARTERS
COMPONENT (A) | TOTAL NOS OF COMPONENTS (B) | DELIVERED ON SITE (C) | BALANCED NOT DELIVERED (B-C) | INSTALLED (D) | BALANCED NOT INSTALLED ON SITE (C-D)
COLUMN | 114 | 17 | 97 | 3 | 15
BEAM | 65 | 19 | 46 | 0 | 19
SLAB | 40 | 12 | 28 | 0 | 12
TOTAL | 179 | 36 | 143 | 3 | 34
BLOCK: KLINIK
Pelaporan

## Slide 38
SUMMARY OF DELIVERY SCHEDULE
8 nos of components delivered
01
02
03
04
29 nos of components delivered
37 nos of components delivered
8 nos of components delivered
62 nos of components will be deliver
60 nos of components will be deliver
56 nos of components delivered
55 nos of components delivered
08
07
06
05
11.10.18
18.10.18
23.10.18
28.10.18
15.1.19
16.12.18
27.11.18
19.11.18
09
21.1.19
60 nos of components will be deliver

## Slide 39
SUMMARY OF INSTALLATION SCHEDULE
16.12.18
2.1.19
7.1.19
12.1.19
14.1.19
BLOCK: KUARTERS
Ground floor column | 100%
1st floor beam | 100%
1st floor slab | 100%
1st floor column | 57%
INSTALLATION WORK’S DONE (until Nov 18)
Install balanced 10% 1st floor slab
Install 1st floor column
Install water tank to roof column
Install roof beam
Install upper roof beam
FINISH
In-situ works by Main Con (topping slab)
In-situ works by Main Con (Beam & slab 2nd floor)
In-situ works by Main Con (beam & slab wt to roof)
In-situ works by Main Con

## Slide 40
SUMMARY OF INSTALLATION SCHEDULE
BLOCK: KUARTERS
Ground floor column | 100%
1st floor beam | 100%
1st floor slab | 100%
1st floor column | 57%
INSTALLATION WORK’S DONE (until 19 DEC 18)
PLANNING |  | ACTUAL | 
DATE | ACTIVITY | DATE | ACTIVITY
16.12.18 | INSTALL BALANCE 10 % SLAB | 13.12.18 | COMPLETE 1ST FLOOR SLAB
02.01.19 | INSTALL 1ST FLOOR COLUMN | 19.12.18 | INSTALL 17/30 1ST FLOOR COLUMN
07.01.19 | INSTALL WATER TANK TO ROOF COLUMN |  | 
12.01.19 | INSTALL ROOF BEAM |  | 
14.01.19 | INSTALL UPPER ROOF BEAM |  | 
14/01/2019 COMPLETE ALL IBS WORK FOR KUARTERS |  |  | 

## Slide 41
SUMMARY OF INSTALLATION SCHEDULE
16.12.18
24.12.18
19.1.19
5.2.19
10.2.19
Install 1st floor column
Install 2nd floor beam
Install hollow core slab
Install 2nd floor column
Install roof beam
In-situ works by Main Con
In-situ works by Main Con
In-situ works by Main Con
BLOCK: KLINIK
START
11.2.19
FINISH
In-situ works by Main Con

## Slide 42
SUMMARY OF INSTALLATION SCHEDULE
BLOCK: KLINIK
1ST floor column | 5%
INSTALLATION WORK’S DONE (until 19 DEC 18)
PLANNING |  | ACTUAL | 
DATE | ACTIVITY | DATE | ACTIVITY
16.12.18 | INSTALL FIRST FLOOR COLUM | 16.12.18 – 19.12.18 | DELIVERY 23 ELEMENT INSTALL 3/68 1ST FLOOR COLUMN
24.12.18 | INSTALL 2ND FLOOR BEAM |  | 
19.01.19 | INSTALL HOLLOW CORE SLAB |  | 
05.02.19 | INSTALL 2ND FLOOR COLUMN |  | 
10.02.18 | INSTALL ROOF BEAM |  | 
11/02/2019 COMPLETE ALL IBS WORK FOR KLINIK |  |  | 

## Slide 43
JANGKAAN MASALAH
(RISIKO)

## Slide 46
Sekian, Terima Kasih
Disediakan oleh:
Jabatan Kerja Raya, Jajahan Pasir Mas Kelantan
Tel: 09 790 8040 | Faks: 09 790 8382 | pasirmas@jkr.gov.my
09 Nov 2020